## Roadmap
ID | Item | Tranche | What it delivers | FURPS | Size | Size pts | Impact | Impact pts | Value per effort | Risk | Status | Depends on | Done when (confirm) | MoSCoW
196 | Re-prove task 154 on main | M0 | A synchronous delegate from a claude-code orchestrator returns after 60 s; the desktop RPI walk passes | R | S |  | High |  |  | Low | Done 2026-09-23 | — | forced-sync delegate → SLEPT (183 s); just walk "rpi strip" → 1 passed | Must
181 | A reconnect keeps the running reply | M0 | Umbrella for 197–200 (plan: docs/2026-09-23-task181-shared-run-plan-v1.md) | R | XL |  | High |  |  | High | In progress | 196 | just walk "reconnect during a Hard turn" → 1 passed | Must
197 | One server-owned AgentManager | M0 | One agent per session across connections; agents with a running turn pinned against eviction | R | M |  | Low |  |  | Med | Done 2026-09-23 | 181 approval | cargo test -p goose --lib task181_shared_ownership → 3 passed | Must
198 | The server owns the run | M0 | Reply stream owned by the server; a reconnect re-attaches and gets the reply exactly once | R | XL |  | High |  |  | High | Rework open (first pass merged) | 197 | cargo test -p goose --test acp_server_test task181_reconnect → 2 passed | Must
199 | Two clients, cancel, permissions, isolation | M1b | Two subscribers, cancel from either, permission hand-over, cwd isolation, eviction pressure (runs beside M1b) | R, F | L |  | Med |  |  | Med | Planned | 198 | cargo test -p goose --test acp_server_test task181_multi_connection → 6 passed | Should
200 | Desktop recovers mid-turn | M0 | Streaming/idle and Stop restored after a reconnect; a walk proves it | R, U | M |  | Med |  |  | Med | Planned | 198 | just walk "reconnect during a Hard turn" → 1 passed; just smoke | Must
M1a | Melody's session tools, headless | M1a | list/start/status tools on the session bridge; server-side authorization; approvals; restart recovery; one manager per repository; new-session notices | F, R | XL |  | Very high |  |  | High | Planned at 200's gate | 181 | cargo test -p goose --test melody_* (7 checks) | Must
M1b | The smallest real Melody | M1b | Her Work tab bound to a persistent session; pin + row at the top of Today; Work toggle; lever removed; one minimal repository manager | F, U | L |  | Very high |  |  | Med | Planned at M1a's gate | M1a | just walk "melody starts a session" → 1 passed | Must
M2 | Companions (manager sessions) | M2 | Harmony, Tempo, Chord: names and marks, companion view, send_to_session, limits, manager role | F | L |  | High |  |  | Med | Planned (conflicts settled 2026-09-23) | M1b + memory PRD conflicts | just walk "friend" → 1 passed | Should
M3 | Visual language app-wide | M3 | DESIGN.md amendments, Heroicons sweep, runtime colours, motion picks, tab polish | U | L |  | High |  |  | Low | Planned at M1b's gate | M1b | DESIGN.md checks; theme-tokens.test.ts; window screenshots at 1512 | Should
P1 | Melody's cost and concurrency budget | M1b | An idle Melody or manager makes no model calls; a combined limit on running managers and workers; seat usage per turn in the ledger | P | M |  | Med |  |  | Low | Planned at M1a's gate | M1a | a test: idle Melody makes 0 model calls over N minutes; the N+1th worker waits | Should
S1 | Diagnosing what Melody starts | M2 | The chain Melody → manager → worker, and why a session she started failed, in Diagnostics and Telemetry | S | M |  | Med |  |  | Low | Planned at M1b's gate | M1b | a walk: a failed worker's cause shows under its manager in Diagnostics | Could
M4 | First run and Settings | M4 | Walkthrough, sign-in via a Terminal tab, Settings route, phone tab order | U, S | M |  | Med |  |  | Low | Planned | M2, M3 | fresh profile → first run → Melody's first message | Could
A | Melody v0.9 alpha | A | Version line 0.9.0-alpha.1; a published GitHub release (task 195); alpha checklist; updater from alpha.1 to alpha.2 proven | S, U | M |  | High |  |  | Med | Planned | all Must/Should/Could | gh release view v0.9.0-alpha.1; just test-full green; alpha.1 → alpha.2 via the updater | Must
T0 | The notebook, live | T0 | ~/Melody: charter, soul, memory index, journal, memories/ (OKF v0.2); weekly health check; lifecycle rules; PRD v2; week-of-use script | R, S | S |  | Med |  |  | Low | Done 2026-09-23 (week of use pending) | — | claude -p in ~/Melody recalls the five check-in steps; week script fixture 4 · 3 · 1 | Must
T1 | Trustworthy job outcomes | T1 | Job identity, land events, outcome precedence, linked rework, dedup, one-tap verdicts in the work ledger | R | M |  | High |  |  | Med | Planned at T0's gate | T0, M1a | pnpm vitest run ledger-outcome; just walk "job verdict" | Should
T2 | Team health, Usage, Team Context | T2 | Team health and Usage tabs; then Team Context (rich editor over memories), Reminders, Clean-up, Companions, Routines | U | L |  | High |  |  | Med | Planned | M1b, M3 | just walk "team health" | Could
T3 | Lifecycle routines | T3 | Weekly check-in, budgeted nightly tidy-up (DREAMS.md), cap check, journal archive, worktree sweep, backup, reminders | R, P | M |  | Med |  |  | Low | Planned | M1b, T0 | fixture: journal byte-identical, ≤25% dropped, stops at budget, idle hour makes no call | Could
T4 | Companion growth | T4 | Test sets from judged jobs, pass^3 charter gate, DORA-style scorecard, time horizon, autonomy ladder | F, R | L |  | High |  |  | Med | Planned | M2, T1 | a regressing fixture proposal shows "scores lower on <task>"; <3 judged jobs → not enough history | Could
Blue cells (Size, Impact) are Claude's estimates, 2026-09-23, from the program plan v2 and task 181's plan; change them from the dropdowns and the points recalculate. Updated 2026-09-23: 0.9 is the one target; team memory T0–T4 joined (docs/2026-09-23-team-memory-program-plan-v2.md); friends are now companions.
Note on J1: Impact points ÷ size points: more value per unit of effort is higher. 181 is the umbrella; its tasks 197–200 carry the effort.

## Scales
Scales (edit the blue points to re-weight)
Size | Points | Meaning | Impact | Points
S | 1 | under a day; one file or a check | Low | 1
M | 2 | a few files, one area | Med | 2
L | 3 | several files, or a broad sweep | High | 3
XL | 5 | core refactor or new subsystem; highest risk | Very high | 5
FURPS: F Functionality (incl. security) · U Usability · R Reliability · P Performance · S Supportability

## By tranche
Tranche | Items | Size pts | Impact pts | Note
M0 |  |  |  | tasks 197, 198, 200 (excludes umbrella 181 and done 196)
M1a
M1b
M2 |  |  |  | companions; conflicts settled 2026-09-23
M3
M4
A |  |  |  | v0.9 alpha
T0 |  |  |  | team memory — in 0.9 since 2026-09-23
T1
T2
T3
T4
Total

## MoSCoW x FURPS
MoSCoW | F | U | R | P | S | Items | Size pts | Note
Must | [7 empty] | 181's umbrella and done 196 excluded
Should
Could
Total